## Sheet1
Time plan - EEA Sensorweb project - EEA/SES/11/001
version 2011-09-16
[5 empty] | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January
Task | Comp | Dependency | Lead | Time est. | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
#34 | WP1 |  | 52N | 6 | bar: September 39 to October 40
#35 | WP1 |  | 52N | 5 | bar: September 39 to October 40
#36 | WP1 |  | Atkins | 10 | bar: September 37 to October 40
#37 | WP1 | #34,#35 | Atkins | 3 | bar: October 41
#38 | WP2 | #35 | con,52N | 5 | bar: October 41 to October 42
#39 | WP2 | #37 | Atkins | 10 | bar: October 43 to November 45
#40 | WP2 | #39 | Atkins | 15 | bar: November 46 to December 49
#41 | WP2 | SOS Extention | Atkins | 0 | bar: December 48
#42 | WP2 | #38,#39,#40,#41 | EEA | 2 | bar: December 50
#43 | WP1 | SOS Extention | 52N | 15 | bar: December 48 to December 51
#44 | WP1 | None | All | 6 | bar: September 36